## Project Profile
Defect Tracking Sheet
TMT/TD05/TMP
Project ID | PRJ_BankingExamPortal_2.1
Project Name | Banking Exam Portal_2.1
Prepared/Modified by | Role | Date of Preparation
Reviewed by | Role | Date of Review
Approved by | Role | Date of Approval
Circulation List
Version Number | 1

## Defect Tracking Sheet
Project ID: | PRJ_BankingExamPortal_2.1 | Project Name : Banking Exam Portal_2.1 | [22 empty] | VERIFIED
Defect Id. | Module name | Defect Summary | Defect Description | Defect Category | Detected in Browser | Environment | Defect Severity | Defect Priority | Detected in Release # | Detected in Build # | Reported Date | Reported By | Assigned To | Status | Review type / Test Cycle | Test Case No. | Fixed By | Fixed Date | Verified Date | Verified By | Verified in Release # | Verified in Build # | Attachements | Comments | REOPENED | Coding | Internal Dev
DF_Bank_Exam_Portal_001 | Bank_Exam_Portal | The mobile number field in the Registration page is found to accept alphabets and special characters also and values more than 10 numbers | Detailed Description: The mobile number field in the Registration page is found to accept alphabets and special characters also Steps To reproduce the bug: 1. Open Browser 2. Enter URL for the website 3. Click on Register link 4. Enter Invalid Mobile number(using alphabets and special characters) 5. Enter other Valid credentials 6. Click on Submit button Actual result observed on running above steps: On executing the above mentioned steps it is observed that the application accepts valid values in the othjer credential fields but also accepts the any data in themobile number field .The application proceeds to the next page.There is no error message shown as expected. | Coding | Internet Explorer | Internal Dev | High | Medium | 1.1 | Build 1.0
|  |  | not as expected as | design |  | 3 GB of RAM | P3 | High | 1.1
Note on A3: A unique number for the Defect Id
Note on B3: Give the name of the module being tested
Note on C3: Summarize the defect in 1 or 2 lines
Note on D3: A detailed description of the defect
Note on E3: Categorize the defect into the one of the values given in the drop down list
Note on F3: Mention the name of the browser the defect was found in.
Note on G3: Mention the environment in which the defect was found.
Note on H3: P0 defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption P1 defect is a defect wherein a function does not work and a tedious work around exists. e.g. One of menu options does not work. P2 defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. P3 defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling. “High” severity defect is a defect wherein the main function of the software does not work. e.g. crash, hang, data corruption, some of the menu functions do not work “Medium” severity defect is a defect wherein the software does useful work but a degree of inconvenience is caused. Correction is not deferrable and easy work around exists. “Low” severity defect is a tolerable defect as corrections are deferrable. E.g. cosmetic problems in user interface like spelling.
Note on I3: Prioritize the defect
Note on J3: Enter the Release # in which the defect was detected.
Note on K3: Enter the Build # in which the defect was detected.
Note on L3: Mention the date the defect was reported
Note on M3: Name of the person who reported the defect.
Note on N3: Name of the person the defect is assigned to.
Note on O3: Can have values: VERIFIED CLOSED FIXED ACT-Active CNR-Could Not be Reproduced NOD- Reported Bug Not a Defect REP- Repeated
Note on P3: Values can be: PPR-Peer to Peer Review PR-Peer Review SR-Self/Programmer Review QPR-10% Quality Probe(Review) RT-Random Testing UTC-Using Test Cases
Note on Q3: Mention the Test Case No that the defect was found while testing
Note on R3: Name of the person who fixed the defect.
Note on S3: Mention the date the defect was Fixed
Note on T3: Mention the date the defect was verified
Note on U3: Name of the person who will be verifying whether the defect has got fixed after the defect has being worked upon
Note on V3: Enter the Release # in which the defect was available for verification
Note on W3: Enter the Build # in which the defect was available for verification
Note on X3: Attach the proofs showing the defect-screenshots,temp files,etc
Note on Y3: Should include all the comments on the defects till date by all touching the defect.It should be captured date wise.